## Project Planner
Project | SEE4ME
|  |  |  | PERIOD IN days | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (Period of completion) | [7 empty] | % Complete (beyond plan)
ACTIVITY |  | PLAN START | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190
MAIN TASKS | SUBTASKS
IDEEAION |  | 2 | 2 | 7 | 100%
COLLECT USER REQUIREMENT |  | 7 | 7 | 8 | 95%
| functional and non functional requirements | 8 | 8 | 2 | 95%
| Actions and features the user needs in the project | 10 | 10 | 3 | 100%
| collect system requirements | 10 | 10 | 1 | 100%
GENERATE SRS |  | 15 | 15 | 7 | 100%
PROJECT DEVELOPMENT PLAN |  | 22 | 22 | 6 | 95%
| project financial estimation budgets | 22 | 22 | 2 | 75%
| identify project development methodologies to be used. | 24 | 24 | 2 | 100%
| project development lifespan | 25 | 25 | 2 | 100%
PROJECT DESIGNS |  | 29 | 32 | 21 | 85%
| split project into modules. | 33 | 33 | 2 | 100%
| come up with low-level designs/wireframes of the project (User Interface) | 35 | 35 | 5 | 100%
| Come up with high-level project designs (User Interface) | 40 | 40 | 7 | 75%
| Come up with Database ERD designs for the project | 47 | 48 | 3 | 80%
| Come up with project workflows like flow charts for each module | 51 | 52 | 4 | 95%
PROJECT IMPLEMENTATIION |  | 55 | 57 | 90 | 10%
| Setup working development environment | 60 | 61 | 2 | 100%
| Download project dependencies | 63 | 63 | 1 | 100%
| Create a project folder arrangements | 64 | 64 | 1 | 100%
| code out the project User interface according to the module | 66 | 66 | 60 | 0%
| code out the backend | 126 | 127 | 30 | 10%
PROJECT TESTING |  | 160 | 160 | 3 | 10%
| begin testing each module | 163 | 163 | 7 | 10%
| perform user-centered testing | 170 | 176 | 14 | 0%
| review feedback from users | 190 | 190 | 7 | 1%
DEPLOYMENT |  | 210 | 220 | 10 | 1%